## Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
1 | Authentication and profile management + Home |  | 65 | 65 | 0 |  | 2024-11-21 | 2024-12-10 |  | 100% | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1.1 | Registration | Gavriel | 17 | 17 | 0 | 1 | 2024-11-21 | 2024-11-25 | 5 | 100%: 100%
1.1.1 | Login | Gavriel | 14 | 14 | 0 | 1 | 2024-11-21 | 2024-11-25 | 5 | 100%: 100%
1.2 | Seeing the profile | Anna | 11 | 11 | 0 | 1 | 2024-11-26 | 2024-11-28 | 3 | 100%: 100%
1.3 | Changing username | Anna | 6 | 6 | 0 | 1 | 2024-11-26 | 2024-11-29 | 4 | 100%: 100%
1.4 | Changing password | Jacopo | 8 | 8 | 0 | 1 | 2024-12-03 | 2024-12-10 | 8 | 100%: 100%
1.5 | Home page | Alessandro | 9 | 9 | 0 | 1 | 2024-11-27 | 2024-11-30 | 4 | 100%: 100%
2 | Trip creation and management, Cities, Expenses |  | 83 | 83 | 0 |  | 2024-12-21 | 2025-01-10 |  | 100% | [21 empty] | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
2,1 | Trip creation | Anna | 14 | 14 | 0 | 2 | 2024-12-23 | 2024-12-28 | 6 | 100% | bar: 23; 27 to 28; 8
2,2 | Seeing the trips | Anna | 8 | 8 | 0 | 2 | 2024-12-30 | 2025-01-08 | 10 | 100% | bar: 30 to 31; 8
2,3 | Searching trips | Alessandro | 6 | 6 | 0 | 2 | 2025-01-09 | 2025-01-10 | 2 | 100% | bar: 9 to 10
2,4 | Seeing the invitations | Alessandro | 5 | 5 | 0 | 2 | 2024-12-29 | 2025-01-02 | 5 | 100% | bar: 29 to 30; 2
2.4.1 | Inviting to a trip | Gavriel | 8 | 8 | 0 | 2 | 2024-12-29 | 2025-01-02 | 5 | 100% | bar: 29 to 30; 2
2.4.2 | Revoking an invitation | Gavriel | 3 | 3 | 0 | 2 | 2025-01-03 | 2025-01-04 | 2 | 100% | bar: 3 to 4
2.4.3 | Accepting an invitation | Gavriel | 2 | 2 | 0 | 2 | 2025-01-04 | 2025-01-04 | 1 | 100% | bar: 4
2.4.4 | Refusing an invitation | Gavriel | 2 | 2 | 0 | 2 | 2025-01-04 | 2025-01-04 | 1 | 100% | bar: 4
2,5 | Removing a participant | Gavriel | 4 | 4 | 0 | 2 | 2025-01-07 | 2025-01-08 | 2 | 100% | bar: 4; 8
2,6 | Leaving a trip | Gavriel | 3 | 3 | 0 | 2 | 2025-01-07 | 2025-01-09 | 3 | 100% | bar: 7 to 8
2,7 | Trip deletion | Alessandro | 2 | 2 | 0 | 2 | 2024-12-28 | 2024-12-28 | 1 | 100% | bar: 28
2,8 | City suggestion | Alessandro | 5 | 5 | 0 | 2 | 2024-12-30 | 2025-01-04 | 6 | 100% | bar: 30; 4
2,9 | Expense creation | Jacopo | 21 | 21 | 0 | 2 | 2025-01-03 | 2025-01-10 | 8 | 100% | bar: 3 to 4; 8 to 10
3 | Trip edit, Schedule, Expenses 2.0 |  | 98 | 98 | 0 |  | 2025-01-13 | 2025-02-02 |  | 100% | [42 empty] | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2
3.2 | Changing a trip's title | Gavriel | 3 | 3 | 0 | 3 | 2025-01-06 | 2025-01-07 | 2 | 100% | bar: 13 to 14
3.2.1 | Changing a trip's dates | Gavriel | 3 | 3 | 0 | 3 | 2025-01-06 | 2025-01-07 | 2 | 100% | bar: 13 to 14
3.2.2 | Changing a trip's destinations | Gavriel | 3 | 3 | 0 | 3 | 2025-01-06 | 2025-01-07 | 2 | 100% | bar: 13 to 14
3.1 | Seeing the schedule | Anna | 7 | 7 | 0 | 3 | 2025-01-06 | 2025-01-09 | 4 | 100% | bar: 13 to 16
3.3 | Schedule filtering | Anna | 1 | 1 | 0 | 3 | 2025-01-08 | 2025-01-09 | 2 | 100% | bar: 15 to 16
3,4 | Activity creation | Alessandro | 4 | 4 | 0 | 3 | 2025-01-08 | 2025-01-09 | 2 | 100% | bar: 15 to 16
3.4.1 | Activity deletion | Alessandro | 2 | 2 | 0 | 3 | 2025-01-08 | 2025-01-10 | 3 | 100% | bar: 15 to 17
3.4.2 | Seeing an activity's details | Alessandro | 5 | 5 | 0 | 3 | 2025-01-08 | 2025-01-09 | 2 | 100% | bar: 15 to 16
3.4.3 | Changing an activity's information | Alessandro | 8 | 8 | 0 | 3 | 2025-01-17 | 2025-01-20 | 4 | 100% | bar: 24 to 27
3,5 | Travel creation | Anna | 4 | 4 | 0 | 3 | 2025-01-07 | 2025-01-09 | 3 | 100% | bar: 14 to 16
3.5.1 | Travel deletion | Anna | 2 | 2 | 0 | 3 | 2025-01-08 | 2025-01-10 | 3 | 100% | bar: 15 to 17
3.5.2 | Seeing a travel's details | Anna | 5 | 5 | 0 | 3 | 2025-01-07 | 2025-01-09 | 3 | 100% | bar: 14 to 16
3.2.3 | Changing a travel's information | Anna | 8 | 8 | 0 | 3 | 2025-01-17 | 2025-01-18 | 2 | 100% | bar: 24 to 25
3.2.4 | Changing a night's place | Anna | 1 | 1 | 0 | 3 | 2025-01-20 | 2025-01-20 | 1 | 100% | bar: 27
3,6 | Accomodation creation | Anna | 3 | 3 | 0 | 3 | 2025-01-20 | 2025-01-21 | 2 | 100% | bar: 27 to 28
3.6.1 | Accomodation deletion | Anna | 1 | 1 | 0 | 3 | 2025-01-23 | 2025-01-23 | 1 | 100% | bar: 30
3.6.2 | Seeing an accomodation's details | Anna | 2 | 2 | 0 | 3 | 2025-01-23 | 2025-01-24 | 2 | 100% | bar: 30 to 31
3.6.3 | Changing an accomodation's information | Anna | 4 | 4 | 0 | 3 | 2025-01-23 | 2025-01-24 | 2 | 100%
3.7 | Changing an expense's title | Jacopo | 2 | 2 | 0 | 3 | 2025-01-13 | 2025-01-15 | 3 | 100% | bar: 13 to 15
3,7,1 | Changing an expense's amount | Jacopo | 7 | 7 | 0 | 3 | 2025-01-13 | 2025-01-15 | 3 | 100% | bar: 13 to 15
3,7,2 | Changing an expense's split | Jacopo | 8 | 8 | 0 | 3 | 2025-01-13 | 2025-01-15 | 3 | 100% | bar: 13 to 15
3,7,3 | Changing an expense's date | Jacopo | 2 | 2 | 0 | 3 | 2025-01-13 | 2025-01-15 | 3 | 100% | bar: 13 to 15
3,7,4 | Delete an expense | Jacopo | 5 | 5 | 0 | 3 | 2025-01-24 | 2025-01-24 | 1 | 100% | bar: 24
3.8 | Seeing balances | Jacopo | 6 | 6 | 0 | 3 | 2025-01-21 | 2025-01-22 | 2 | 100% | bar: 21 to 22
3,8,1 | Seeing debts/credits | Jacopo | 2 | 2 | 0 | 3 | 2025-01-21 | 2025-01-27 | 7 | 100% | bar: 21 to 22; 27
4 | Chat, Photos, Event map, Waether, Fix |  | 81 | 81 | 0 |  | 2025-03-01 | 2025-03-21 |  | 100% | [63 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
4.1 | Debt compensation | Jacopo | 6 | 6 | 0 | 4 | 2025-03-11 | 2025-03-11 | 1 | 100%
4.2 | Seeing an activity's map | Alessandro | 5 | 5 | 0 | 4 | 2025-03-04 | 2025-03-05 | 2 | 100% | bar: 4 to 5
4.3 | Seeing a travel's map | Alessandro | 4 | 4 | 0 | 4 | 2025-03-04 | 2025-03-05 | 2 | 100% | bar: 4 to 5
4.4 | Create WebSocket connection | Jacopo | 21 | 21 | 0 | 5 | 2025-03-01 | 2025-03-21 | 21 | 100% | bar: 1 to 3; 20 to 21
4,4,1 | Send/Read message | Jacopo | 6 | 6 | 0 | 5 | 2025-03-02 | 2025-03-03 | 2 | 100% | bar: 2 to 3
4.5 | Check Online Status | Jacopo | 10 | 10 | 0 | 5 | 2025-03-16 | 2025-03-19 | 4 | 100% | bar: 16 to 17; 19
4.6 | Seeing the photos | Anna | 6 | 6 | 0 | 5 | 2025-03-06 | 2025-03-07 | 2 | 100% | bar: 6 to 14
4,6,1 | Uploading a photo | Anna | 8 | 8 | 0 | 5 | 2025-03-06 | 2025-03-07 | 2 | 100% | bar: 6 to 14
4,6,2 | Deleting a photo | Anna | 2 | 2 | 0 | 5 | 2025-03-08 | 2025-03-08 | 1 | 100%
4.7 | Weather | Gavriel | 5 | 5 | 0 | 5 | 2025-03-11 | 2025-03-11 | 1 | 100%
4.8 | Migration Authentication | Gavriel | 8 | 8 | 0 | 5 | 2025-03-12 | 2025-03-13 | 2 | 100%
| BURNDOWN DATA | TOTAL HOURS | 327 | 327 | 0 | 84 | 3.8929 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 327 | 323.1071 | 319.2143 | 315.3214 | 311.4286 | 307.5357 | 303.6429 | 299.75 | 295.8571 | 291.9643 | 288.0714 | 284.1786 | 280.2857 | 276.3929 | 272.5 | 268.6071 | 264.7143 | 260.8214 | 256.9286 | 253.0357 | 249.1429 | 245.25 | 241.3571 | 237.4643 | 233.5714 | 229.6786 | 225.7857 | 221.8929 | 218 | 214.1071 | 210.2143 | 206.3214 | 202.4286 | 198.5357 | 194.6429 | 190.75 | 186.8571 | 182.9643 | 179.0714 | 175.1786 | 171.2857 | 167.3929 | 163.5 | 159.6071 | 155.7143 | 151.8214 | 147.9286 | 144.0357 | 140.1429 | 136.25 | 132.3571 | 128.4643 | 124.5714 | 120.6786 | 116.7857 | 112.8929 | 109 | 105.1071 | 101.2143 | 97.3214 | 93.4286 | 89.5357 | 85.6429 | 81.75 | 77.8571 | 73.9643 | 70.0714 | 66.1786 | 62.2857 | 58.3929 | 54.5 | 50.6071 | 46.7143 | 42.8214 | 38.9286 | 35.0357 | 31.1429 | 27.25 | 23.3571 | 19.4643 | 15.5714 | 11.6786 | 7.7857 | 3.8929
[10 empty] | ESTIMATE | 327 | 319 | 311 | 307 | 303 | 296 | 291 | 286 | 281 | 276 | 270 | 270 | 270 | 269 | 268 | 267 | 266 | 265 | 264 | 263 | 262 | 262 | 262 | 262 | 257 | 257 | 257 | 257 | 253 | 247 | 243 | 231 | 227 | 227 | 223 | 216 | 205 | 205 | 205 | 199 | 189 | 181 | 179 | 168 | 154 | 137 | 127 | 123 | 123 | 123 | 123 | 119 | 116 | 116 | 108 | 105 | 102 | 95 | 93 | 93 | 86 | 81 | 81 | 81 | 75 | 68 | 61 | 56 | 52 | 44 | 38 | 36 | 36 | 36 | 25 | 21 | 17 | 17 | 17 | 13 | 9 | 9 | 7 | 4 | 13970
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 8 | 8 | 4 | 4 | 7 | 5 | 5 | 5 | 5 | 6 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 4 | 6 | 4 | 12 | 4 | 0 | 4 | 7 | 11 | 0 | 0 | 6 | 10 | 8 | 2 | 11 | 14 | 17 | 10 | 4 | 0 | 0 | 0 | 4 | 3 | 0 | 8 | 3 | 3 | 7 | 2 | 0 | 7 | 5 | 0 | 0 | 6 | 7 | 7 | 5 | 4 | 8 | 6 | 2 | 0 | 0 | 11 | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 2 | 3 | 4 | 327
[10 empty] | HRS REMAINING | 319 | 311 | 307 | 303 | 296 | 291 | 286 | 281 | 276 | 270 | 270 | 270 | 269 | 268 | 267 | 266 | 265 | 264 | 263 | 262 | 262 | 262 | 262 | 257 | 257 | 257 | 257 | 253 | 247 | 243 | 231 | 227 | 227 | 223 | 216 | 205 | 205 | 205 | 199 | 189 | 181 | 179 | 168 | 154 | 137 | 127 | 123 | 123 | 123 | 123 | 119 | 116 | 116 | 108 | 105 | 102 | 95 | 93 | 93 | 86 | 81 | 81 | 81 | 75 | 68 | 61 | 56 | 52 | 44 | 38 | 36 | 36 | 36 | 25 | 21 | 17 | 17 | 17 | 13 | 9 | 9 | 7 | 4 | 0 | 13643
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
High | 1 | Authentication | Registration | As a future user, I want to register via email and password, to begin using the application. | Gavriel | 17 | Done |  | Not Started | 1
High | 1 | Authentication | Login | As a user, I want to login, to access the application's features. | Gavriel | 14 | Done |  | In Progress | 2
Low | 1 | Authentication | Seeing the profile | As a user, I want to access my profile, to see my information. | Anna | 11 | Done |  | Done | 8
Low | 1 | Authentication | Changing username | As a user, I want to modify my username. | Anna | 6 | Done |  |  | 16
Medium | 1 | Authentication | Changing password | As a user, I want to modify my password. | Jacopo | 8 | Done |  |  | 24
High | 1 | Main | Home | Create home page for the software | Alessandro | 9 | Done
High | 2 | Trip | Trip creation | As a user, I want to create a Trip, to start planning my trip. | Anna | 14 | Done |  |  | 40
High | 2 | Trip | Seeing the trips | As a user, I want to see all my trips. | Anna | 8 | Done |  |  | 80
Low | 2 | Trip | Searching trips | As a user, I want to search my trips by title or destination. | Alessandro | 6 | Done
Medium | 2 | Trip | Seeing the invitations | As a user, I want to see my pending invitations to some trips. | Alessandro | 5 | Done
High | 2 | Trip | Inviting to a trip | As a trip creator, I want to invite other users to my trip, to share trip information with them. | Gavriel | 8 | Done
Medium | 2 | Trip | Revoking an invitation | As a trip creator, I want to revoke an invitation that has been sent. | Gavriel | 3 | Done
Medium | 2 | Trip | Accepting an invitation | As a user, I want to accept an invitation to a trip. | Gavriel | 2 | Done
Low | 2 | Trip | Refusing an invitation | As a user, I want to refuse an invitation to a trip. | Gavriel | 2 | Done
Medium | 2 | Trip | Removing a participant | As a trip creator, I want to remove a participant from my trip. | Gavriel | 4 | Done
Medium | 2 | Trip | Leaving a trip | As a trip participant, I want to leave the trip. | Gavriel | 3 | Done
Medium | 2 | Trip | Trip deletion | As a trip creator, I want to delete a Trip. | Alessandro | 2 | Done
Medium | 2 | Trip | City suggestion | As a user who's creating or updating a trip, I want to see be suggested names of cities | Alessandro | 5 | Done
High | 2 | Expense | Expense creation | As a trip participant, I want to create a new expense, to settle up at the end of the trip | Jacopo | 21 | Done
Low | 3 | Trip | Changing a trip's title | As a trip participant, I want to modify the trip's title. | Gavriel | 3 | Done
Medium | 3 | Trip | Changing a trip's dates | As a trip participant, I want to modify the trip's dates. | Gavriel | 3 | Done
Medium | 3 | Trip | Changing a trip's destinations | As a trip participant, I want to modify the trip's destinations. | Gavriel | 3 | Done
High | 3 | Trip | Seeing the schedule | As a trip participant, I want to see the trip's schedule. | Anna | 7 | Done
Low | 3 | Trip | Schedule filtering | As a trip participant, I want to filter my schedule by a specific day. | Anna | 1 | Done
High | 3 | Activities | Activity creation | As a trip participant, I want to add an activity to a trip's schedule | Alessandro | 4 | Done
Medium | 3 | Activities | Activity deletion | As a trip participant, I want to delete an activity from a trip's schedule | Alessandro | 2 | Done
Medium | 3 | Activities | Seeing an activity's details | As a trip participant, I want to see the details of an activity from the schedule. | Alessandro | 5 | Done
Low | 3 | Activities | Changing an activity's information | As a trip participant, I want to modify an activity's name, time, place, date, address and additional information. | Alessandro | 8 | Done
High | 3 | Activities | Travel creation | As a trip participant, I want to add a travel to a trip's schedule | Anna | 4 | Done
Medium | 3 | Activities | Travel deletion | As a trip participant, I want to delete a travel from a trip's schedule | Anna | 2 | Done
Low | 3 | Activities | Seeing a travel's details | As a trip participant, I want to see the details of a travel from the schedule. | Anna | 5 | Done
Medium | 3 | Activities | Changing a travel's information | As a trip participant, I want to modify a travel's name, departure time, arrival time, departure place, arrival place, date, and additional information. | Anna | 8 | Done
Medium | 3 | Activities | Changing a night's place | As a trip participant, I want to change the main location of a night | Anna | 1 | Done
High | 3 | Activities | Accomodation creation | As a trip participant, I want to create an accomodation spanning several nights, to save information about it | Anna | 3 | Done
Medium | 3 | Activities | Accomodation deletion | As a trip participant, I want to delete an accomodation | Anna | 1 | Done
Medium | 3 | Activities | Seeing an accomodation's details | As a trip participant, I want to see the details of a night's accomodation | Anna | 2 | Done
Medium | 3 | Activities | Changing an accomodation's information | As a trip participant, I want to modify an accomodation's name, check-in and check-out time, dates, contacts, address and additional information. | Anna | 4 | Done
Low | 3 | Expense | Changing an expense's title | As a trip participant, I want to change the title of an expense | Jacopo | 2 | Done
Low | 3 | Expense | Changing an expense's amount | As a trip participant, I want to change the mount of an expense | Jacopo | 7 | Done
Low | 3 | Expense | Changing an expense's split | As a trip participant, I want to change the split of an expense | Jacopo | 8 | Done
Low | 3 | Expense | Changing an expense's date | As a trip participant, I want to change the date of an expense | Jacopo | 2 | Done
Medium | 3 | Expense | Delete an expense | As a trip participant, I want to delete an expense | Jacopo | 5 | Done
Medium | 3 | Expense | Seeing balances | As a trip participant, I want to see how much I spent during the trip | Jacopo | 6 | Done
Medium | 3 | Expense | Seeing debts/credits | As a trip participant, I want to know who I have to pay back | Jacopo | 2 | Done
Medium | 4 | Expense | Debt compensation | As a trip participant, I want to settle my debts | Jacopo | 6 | Done
Low | 4 | Activities | Seeing an activity's map | As a trip participant, I want to see a map with a marker on the activity's address. | Alessandro | 5 | Done
Low | 4 | Activities | Seeing a travel's map | As a trip participant, I want to see a map with a marker on the travel's departure address | Alessandro | 4 | Done
Medium | 4 | Chat | Send/Read message | As a trip participant, I want to see the message sent in the group chat in real time, As a trip participant, I want to send a message to the others participants in a group chat | Jacopo | 6 | Done
Low | 4 | Chat | Check Online Status | As a Trip Partecipant I want to see if any other participant is online | Jacopo | 10 | Done
Medium | 4 | Photos | Seeing the photos | As a trip participant, I want to see the photos of a trip uploaded by me and the other participants | Anna | 6 | Done
Medium | 4 | Photos | Uploading a photo | As a trip participant, I want to upload a photo of a trip | Anna | 8 | Done
Low | 4 | Photos | Deleting a photo | As a trip participant, I want to delete a photo of a trip | Anna | 2 | Done
Low | 4 | Trip | Weather | As a trip participant, I want to see the weather prediction for every day of the trip, to better plan my activities | Gavriel | 5 | Done
High | 4 | Authentication | Migration Authentication | Migrate authentication to another container | Gavriel | 8 | Done

## User Stories or Tasks
SCRUM PROJECT MANAGEMENT GANTT CHART
USER STORIES or TASKS
TASK TITLE | TASK DESCRIPTION | ADDED BY | DATED ADDED
Registration | As a future user, I want to register via email and password, to begin using the application. | Gavriel | 2024-11-21
Login | As a user, I want to login, to access the application's features. | Gavriel | 2024-11-21
Seeing the profile | As a user, I want to access my profile, to see my information. | Anna | 2024-11-21
Changing username | As a user, I want to modify my username. | Anna | 2024-11-21
Changing password | As a user, I want to modify my password. | Jacopo | 2024-11-21
Home | Create home page for the software | Alessandro | 2024-11-21
Trip creation | As a user, I want to create a Trip, to start planning my trip. | Anna | 2024-12-21
Seeing the trips | As a user, I want to see all my trips. | Anna | 2024-12-21
Searching trips | As a user, I want to search my trips by title or destination. | Alessandro | 2024-12-21
Seeing the invitations | As a user, I want to see my pending invitations to some trips. | Alessandro | 2024-12-21
Inviting to a trip | As a trip creator, I want to invite other users to my trip, to share trip information with them. | Gavriel | 2024-12-21
Revoking an invitation | As a trip creator, I want to revoke an invitation that has been sent. | Gavriel | 2024-12-21
Accepting an invitation | As a user, I want to accept an invitation to a trip. | Gavriel | 2024-12-21
Refusing an invitation | As a user, I want to refuse an invitation to a trip. | Gavriel | 2024-12-21
Removing a participant | As a trip creator, I want to remove a participant from my trip. | Gavriel | 2024-12-21
Leaving a trip | As a trip participant, I want to leave the trip. | Gavriel | 2024-12-21
Trip deletion | As a trip creator, I want to delete a Trip. | Alessandro | 2024-12-21
City suggestion | As a user who's creating or updating a trip, I want to see be suggested names of cities | Alessandro | 2024-12-21
Expense creation | As a trip participant, I want to create a new expense, to settle up at the end of the trip | Jacopo | 2024-12-21
Changing a trip's title | As a trip participant, I want to modify the trip's title. | Gavriel | 2025-01-13
Changing a trip's dates | As a trip participant, I want to modify the trip's dates. | Gavriel | 2025-01-13
Changing a trip's destinations | As a trip participant, I want to modify the trip's destinations. | Gavriel | 2025-01-13
Seeing the schedule | As a trip participant, I want to see the trip's schedule. | Anna | 2025-01-13
Schedule filtering | As a trip participant, I want to filter my schedule by a specific day. | Anna | 2025-01-13
Activity creation | As a trip participant, I want to add an activity to a trip's schedule | Alessandro | 2025-01-13
Activity deletion | As a trip participant, I want to delete an activity from a trip's schedule | Alessandro | 2025-01-13
Seeing an activity's details | As a trip participant, I want to see the details of an activity from the schedule. | Alessandro | 2025-01-13
Changing an activity's information | As a trip participant, I want to modify an activity's name, time, place, date, address and additional information. | Alessandro | 2025-01-13
Travel creation | As a trip participant, I want to add a travel to a trip's schedule | Anna | 2025-01-13
Travel deletion | As a trip participant, I want to delete a travel from a trip's schedule | Anna | 2025-01-13
Seeing a travel's details | As a trip participant, I want to see the details of a travel from the schedule. | Anna | 2025-01-13
Changing a travel's information | As a trip participant, I want to modify a travel's name, departure time, arrival time, departure place, arrival place, date, and additional information. | Anna | 2025-01-13
Changing a night's place | As a trip participant, I want to change the main location of a night | Anna | 2025-01-13
Accomodation creation | As a trip participant, I want to create an accomodation spanning several nights, to save information about it | Anna | 2025-01-13
Accomodation deletion | As a trip participant, I want to delete an accomodation | Anna | 2025-01-13
Seeing an accomodation's details | As a trip participant, I want to see the details of a night's accomodation | Anna | 2025-01-13
Changing an accomodation's information | As a trip participant, I want to modify an accomodation's name, check-in and check-out time, dates, contacts, address and additional information. | Anna | 2025-01-13
Changing an expense's title | As a trip participant, I want to change the title of an expense | Jacopo | 2025-01-13
Changing an expense's amount | As a trip participant, I want to change the mount of an expense | Jacopo | 2025-01-13
Changing an expense's split | As a trip participant, I want to change the split of an expense | Jacopo | 2025-01-13
Changing an expense's date | As a trip participant, I want to change the date of an expense | Jacopo | 2025-01-13
Delete an expense | As a trip participant, I want to delete an expense | Jacopo | 2025-01-13
Seeing balances | As a trip participant, I want to see how much I spent during the trip | Jacopo | 2025-01-13
Seeing debts/credits | As a trip participant, I want to know who I have to pay back | Jacopo | 2025-01-13
Debt compensation | As a trip participant, I want to settle my debts | Jacopo | 2025-03-01
Seeing an activity's map | As a trip participant, I want to see a map with a marker on the activity's address. | Alessandro | 2025-03-01
Seeing a travel's map | As a trip participant, I want to see a map with a marker on the travel's departure address | Alessandro | 2025-03-01
Send/Read message | As a trip participant, I want to see the message sent in the group chat in real time, As a trip participant, I want to send a message to the others participants in a group chat | Jacopo | 2025-03-01
Check Online Status | As a Trip Partecipant I want to see if any other participant is online | Jacopo | 2025-03-01
Seeing the photos | As a trip participant, I want to see the photos of a trip uploaded by me and the other participants | Anna | 2025-03-01
Uploading a photo | As a trip participant, I want to upload a photo of a trip | Anna | 2025-03-01
Deleting a photo | As a trip participant, I want to delete a photo of a trip | Anna | 2025-03-01
Weather | As a trip participant, I want to see the weather prediction for every day of the trip, to better plan my activities | Gavriel | 2025-03-01
Migration Authentication | Migrate authentication to another container | Gavriel | 2025-03-01