## Sheet1
Scaling/Adjusting Factor | Characteristic/Feature | Value for Factor | Value of Scaling/Adjusting factor | Notes | enum value | MAPPING ENUM VALUE
PREC |  |  | nominal |  | 3.5 | enum | valuee
| Organizational understanding of product objectives | low |  | few experience on similar projects | 2 | very low | 1
| Experience in working with related software systems | low |  | few experience on similar projects | 2 | low | 2
| Concurrent development of associated new hardware and operational procedures | high |  | project doesn’t need new hardwares And the procedures are not so innovative | 4 | nominal | 3
| Need for innovative data processing architectures, algorithms | extra high |  | really minimal need of innovative algorithms And data structures | 6 | high | 4
FLEX |  |  | high |  | 4.6667 | very high | 5
| Need for software conformance with Preestablished requirements | high |  | we proposed project, we have setted some Requirements but they are not too strict | 4 | extra high | 6
| Need for software conformance with external interface specifications | extra high |  | no external interfaces to interact with | 6
| Combination of inflexibilities above with premium on early completion | high |  | we have all the time, still we need to graduate So there are some temporal constraints | 4
RESL |  |  | low |  | 2.8571
| Risk Management Plan identifies all critical risk items, establishes milestones for resolving them by PDR or LCA. | low |  | we don’t have a structured plan for risk Management | 2
| Schedule, budget, and internal milestones through PDR or LCA compatible with Risk Management Plan. | high |  | since the plan is not structured there are not Too much problems of compatibility with Budget, schedule… | 4
| Percent of development schedule devoted to establishing architecture, given general product objectives. | low |  | we spent few time on the architecture since The project should be not so challenging | 2
| Percent of required top software architects available to project. | very low |  | since we didn’t graduated yet in master Degree none of us can be considered A top software architect | 1
| Tool support available for resolving risk items, developing and verifying architectural specs. | high |  | We think that tools offered by jetbrains Like intellij and youtrack offer a very good Service for supporting the project development | 4
| Level of uncertainty in key architecture drivers: mission, user interface, COTS, hardware, technology, performance. | high |  | we spent a cospicuous part of project time Projecting good interfaces | 4
| Number and criticality of risk Items | nominal |  | in the pproject there are some parts that Can be considered critical | 3
TEAM |  |  | nominal |  | 3.25
| Consistency of stakeholder objectives and cultures | nominal |  | we think we have a good consistency of Our objectives but we are not always On the same line | 3
| Ability, willingness of stakeholders to accommodate other stakeholders’ objectives | high |  | we are good with accomodating requests of each other | 4
| Experience of stakeholders in operating as a team | nominal |  | we know each other since 3 years but we Didn’t have many times to work as a team | 3
| Stakeholder teambuilding to achieve shared vision and Commitments | nominal |  | we are friends and we use to hang out Some times but it is not this much as A teambuilding | 3
PMAT |  |  | low |  | #N/A
| kpa | low |  | EPML = ~0.8 | 2
#N/A
RELY |  |  | low |  | #N/A
| value | low |  | it is not really a problem if the software is not Available for some time, no risks for people, Only little inconvinience | 2
DATA |  |  | very high |  | #N/A
| value D/P | very high |  | our database grows up pretty fast since we are managing both chat and attachments, we extimated D/P = ~1600 using FP converting to java SLOC And dividing the expected size of the Database with The resulting value | 5
CPLX |  |  | low |  | 2.2
| Control Operations | nominal |  | we are using microservices split into docker containers which increase Complexity of control operations | 3
| Computational Operations | very low |  | no complex computational operations, only Simple | 1
| Device dependent Operations | low |  | no particular I/O devices needed, I/O done using REST API | 2
| Data Management Operations | low |  | no too complex data management operations, still some subsetting is Required for few functionalities | 2
| User Interface Management Operations | nominal |  | used simple GUI with some widgets to Enhance user interaction with the Software | 3
RUSE |  |  | low |  | #N/A
| value | low |  | we don’t plan to reuse the components | 2
DOCU |  |  | low |  | #N/A
| value | low |  | some life-cycle needs could be uncovered By the documentation | 2
TIME |  |  | nominal |  | #N/A
| value | nominal |  | we didn’t really have time constraints, so we Leave this to nominal value | 3
STOR |  |  | nominal |  | #N/A
| value | nominal |  | we didn’t really have storage constraints, so we Leave this to nominal value | 3
PVOL |  |  | low |  | #N/A
| value | low |  | the platform is really stable, we are also using docker containers which allow execution of the Software over every OS | 2
ACAP |  |  | low |  | #N/A
| value | low |  | we have a limited experience in analysis of requirements and design | 2
PCAP |  |  | low |  | #N/A
| value | low |  | we are good at programming but with no Previous experience in working as a team on Such a project | 2
PCON |  |  | very high |  | #N/A
| value | very high |  | this because our team is always the same, Not changing members | 5
APEX |  |  | very low |  | #N/A
| value | very low |  | we never had experience with this type of Application | 1
PLEX |  |  | very low |  | #N/A
| value | very low |  | we are not so experienced with many Technologies we used (less than 6 months of Experience) | 1
LTEX |  |  | nominal |  | #N/A
| value | nominal |  | we have a lot of experience with most of Languages and tools we used, we evaluated this Effort multiplier as mean of experience we Have among all tools | 3
TOOL |  |  | nominal |  | #N/A
| value | nominal |  | the tools we used are very usefull with big Part of the software lifecycle (intellij, youtrack, Balsamiq…), we consider them as basic lifecycle tools, Moderately integrated | 3
SITE |  |  | nominal |  | 3
| Collocation Descriptors | high |  | we are all in same city, some times we can also Work as fully collocated but most of times it Doesn’t happen | 4
| Communications Descriptors | low |  | we communicate through phones | 2
SCED |  |  | nominal |  | #N/A
| value | nominal |  | since we have not real constraints on time | 3